WiFi CSI presence sensing

Design and project plan

Date: 2026-08-17

Owner: Justin

Status: Draft — awaiting review, nothing started

# 1. Goal

Detect human movement and presence in a rectangular room using WiFi signals, with no cameras and no wearables. First application: automatically turn lights off when a room has been empty for N minutes.

v1 scope: movement detection in one room, driving one lighting automation.

Out of scope for v1: people counting, pose estimation, multi-room.

# 2. Why this is feasible

Verified during design on 2026-08-17:

| Claim | Source | Note |
| --- | --- | --- |
| Crowd counting ~86.4% for 5 or fewer people | DeepCount (arXiv 1903.05316) | CNN + LSTM on CSI |
| Crowd counting 92.8% for 10 or fewer people | WiCount | Deep learning |
| 10-shot domain adaptation, MAE 0.44 | arXiv 2601.02203 (Jan 2026) | Adapter modules; solves per-room retraining |
| Motion detection F1 above 96% | ESPectre ML detector | On-device, no calibration |
| Presence detection 82.3% | RuView v2 encoder | An earlier "100%" claim was retracted |

Key reframe: the lighting use case needs binary presence, not counting. A room with 20 people is the easiest case for presence, because the signal is enormous. The crowd-size limits that dominate the research literature do not apply to this project.

# 3. Prior art and the gap

- ESPectre — 8,963 stars, actively developed, GPLv3. ESP32 + ESPHome + Home Assistant. This is the easy path and covers v1 entirely.

- RuView — 89.8k stars, MIT, Rust. Far more capable (breathing, heart rate, counting) but a much heavier toolchain.

- Espressif esp-csi — the official CSI toolkit.

## The open gap

ESPectre detects motion, not presence. Its documentation describes a 2-state IDLE/MOTION model. A person sitting still reads as empty, so the lights go off on them.

Pull request #112 implemented a 0.08 to 0.6 Hz breathing bandpass (cascaded Butterworth plus EMA) to fix exactly this. It was not merged. The maintainer gave four reasons:

- The signal was computed but never integrated into the detection pipeline.

- No precision or recall evidence on stationary scenarios — only signal stability was tested.

- Incomplete reset paths and move semantics.

- The project requires Python (micro-espectre) prototyping before any C++ port.

It went stale for about three months and auto-closed on 2026-06-29. The missing piece is validation evidence, not an algorithm. That is this project’s contribution opportunity.

# 4. Materials

## Buy (about $10 to $15)

☐  1x ESP32-C6-DevKit — $6 to $10. Chosen over the S3 and C5 because of an open watchdog-reset bug with MQTT on the S3, an open WiFi connection issue on the C5, and because the C6 is tested by both ESPectre and RuView.

☐  1x USB cable matching the board, usually USB-C.

## Already have

☐  2.4GHz WiFi router — no modification needed.

☐  A computer to flash the board and host the software.

## Do not buy

- Cognitum Seed ($140) — persistent memory and attestation, not better sensing.

- A laptop WiFi card will not work. Consumer WiFi gives RSSI only, not CSI.

## Optional later

- A second ESP32-C6 (about $10) for Layout B coverage.

- 3 to 6 ESP32-S3 boards (about $54) for a full mesh.

# 5. Software

## Path A — ESPectre (easy, no coding). Start here.

☐  Home Assistant running on a Raspberry Pi, PC, or NAS.

☐  Google Chrome, required for the Web Serial API.

Firmware: download the .bin from the ESPectre releases page and flash it via ESPConnect in Chrome. Set up WiFi over BLE using the Home Assistant Companion app, or through web.esphome.io, or via the captive portal. The device then auto-discovers in Home Assistant over the ESPHome native API, so no MQTT is needed.

## Path B — ESPHome CLI (needed from Phase 2)

☐  Python 3.12, not 3.14, which has known ESPHome issues.

☐  ESPHome 2026.5.0 or newer.

☐  The examples/espectre-c6.yaml file from the repository.

## Path C — RuView (optional, later)

☐  Rust 1.85 or newer.

☐  The ESP-IDF toolchain.

☐  Python and esptool.

Try it free first with: docker run -p 3000:3000 ruvnet/wifi-densepose:latest

Both ESPectre and RuView run on the same board. Flashing is reversible, so there is no lock-in.

# 6. Room layout

Sensing happens on the link between the router and the ESP32, not in a radius around the board. Aim the link across where people actually walk. A link is blind to motion along it and sensitive to motion across it.

## Layout A — one link (start here)

+-----------------------------------------+

|                                         |

|                              +--------+ |

|                          .-' | ESP32  | |

|                      .-'     +--------+ |

|                  .-'                    |

|              .-'   <-- sensing link     |

|          .-'                            |

| +--------+                              |

| | router |                              |

| +--------+                              |

|                                         |

+-----------------------------------------+

Weak spots: the top-left and bottom-right corners.

## Layout B — two links (better coverage, about $10 more)

+-----------------------------------------+

|                                         |

|                              +--------+ |

|                          .-' | ESP32  | |

|                      .-'     +--------+ |

| +--------+       .-'                    |

| | router |----->                        |

| +--------+       '-.                    |

|                      '-.     +--------+ |

|                          '-. | ESP32  | |

|                              +--------+ |

+-----------------------------------------+

Two links cross the room at different angles and cover each other’s blind spots.

## Distance constraints

- Optimal distance is 3 to 8 m from the router.

- Performance degrades beyond 10 to 15 m.

- Metal and reinforced concrete reduce sensitivity.

## System architecture

Router sends WiFi. The ESP32-C6 reads CSI on the link between them. That feeds a motion detector (works today) and, once built, a breathing detector (Phase 2 to 3). Both feed the Home Assistant room state, which turns the lights off after N minutes of emptiness. The two detectors fuse as an OR at the state level: motion catches someone walking in, breathing catches someone sitting still.

# 7. Phases

## Phase 0 — Baseline (one weekend)

☐  Run the RuView Docker demo to see what the output looks like. Costs nothing.

☐  Order the ESP32-C6.

☐  Get Home Assistant running.

☐  Flash ESPectre via ESPConnect in Chrome.

☐  Provision WiFi and confirm auto-discovery in Home Assistant.

☐  Enable the ML detector.

☐  Position the board per Layout A and tune per TUNING.md.

☐  Write the automation: no motion for N minutes turns the lights off.

☐  Verify: walk through the link, watch the movement score climb, confirm the lights turn off after the timeout.

At the end of Phase 0 the original goal is complete. Everything after this is research.

## Phase 1 — Characterize the failure (1 to 2 weeks)

☐  Build the raw CSI logger before collecting anything.

☐  Sit still deliberately: reading, studying, watching something.

☐  Log every false "empty" with timestamps.

☐  Record ground truth in three classes: empty, present-moving, present-still.

Deliverable: a labeled dataset of the stationary-person failure, specific to this room. Nobody else has this.

## Phase 2 — Rebuild the breathing detector in Python (2 to 3 weeks)

☐  Work in micro-espectre. Python only, no C++. This rule is what killed PR #112.

☐  Implement the 0.08 to 0.6 Hz bandpass (4.8 to 36 breaths per minute), using the PR #112 coefficients as reference.

☐  Output a breathing score per window.

☐  Validate against the Phase 1 recordings.

## Phase 3 — Validation, the part that was actually missing (2 to 4 weeks)

☐  Measure precision and recall for stationary presence.

☐  Compare motion-only against motion-plus-breathing and report the lift.

☐  Evaluate only on windows where the motion detector says idle. That is the scenario slice the maintainer asked about.

☐  Tune the threshold for asymmetric cost: a false "empty" on a still person is far worse than a few extra minutes of lights.

Deliverable: the evaluation report PR #112 never produced.

## Phase 4 — Integrate and contribute

☐  Wire the breathing score into the detection pipeline as a real user-facing option, not just an exposed number.

☐  Open a Python-only pull request with the evaluation results attached.

☐  Note that ESPectre is GPLv3, so derivative work inherits that license.

# 8. The extensibility requirement

Log raw CSI from day one, not just the motion decision.

If only "motion: true" is stored, everything is thrown away. With timestamped raw CSI plus labels, every future extension becomes a replay over data already collected rather than a new collection campaign.

☐  Keep a rolling capture of raw CSI frames with timestamps.

☐  Keep a separate ground-truth annotation log.

☐  Store in data/, one file per session.

## Extension ladder

- Movement — variance over CSI amplitude. This is v1.

- Presence — add the breathing band. This is the ESPectre gap.

- Zone — with two or more links, compare which is disturbed to infer location.

- Counting — regression on aggregate statistics. About 5 people reliably, 10 with effort.

- Activity — classify walking, sitting, or falling from temporal patterns.

# 9. Open questions and risks

| Item | Status |
| --- | --- |
| Has anyone forked ESPectre to retry breathing detection? | Unverified — check forks and open PRs before Phase 2 |
| Does WiMANS "0 active users" mean nobody present, or present but idle? | Unverified — matters only if public data is used |
| Can Home Assistant and Nexmon CSI share one Raspberry Pi? | Unverified — monitor mode likely conflicts |
| Phase 1 pace | Depends on patiently capturing failures; cannot be rushed |
| A $15 mmWave sensor solves the lighting problem outright | Accepted tradeoff — this project is for the learning and the contribution |

# 10. Alternatives considered and rejected

- mmWave radar at 60GHz — better spatial resolution, $30 to $100. The right answer for pure reliability, rejected because it does not use existing WiFi and is not the project.

- Raspberry Pi with Nexmon CSI — richer data (80MHz, 4 streams) but firmware patching and 5 to 8 times the cost. Reconsider only if the ESP32 path fails.

- Router firmware on an ASUS RT-AC86U — no extra device, but reflashing the household router is unacceptable risk.

- Public datasets only — no hardware needed, but no Phase 1 and no deployment.

- Device presence on the router — free and works today, but it tracks phones rather than people and cannot tell which room.

# 11. Sources

- ESPectre — github.com/francescopace/espectre

- ESPectre PR #112 (breathing) — github.com/francescopace/espectre/pull/112

- RuView — github.com/ruvnet/RuView

- Espressif esp-csi — github.com/espressif/esp-csi

- DeepCount — arxiv.org/abs/1903.05316

- Domain adaptation with adapters — arxiv.org/pdf/2601.02203

- WiMANS — arxiv.org/pdf/2604.16572

- Nexmon CSI — dl.acm.org/doi/10.1145/3349623.3355477